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Capital Contract Change Orders
Report to the Board of Trustees 
September 17, 2026




In May 2026, the Board of Trustees reaffirmed delegated authority to the Comptroller to approve change orders to university contracts and purchase agreements. Board-approved construction contracts with change orders exceeding $1,000,000, but not exceeding $5,000,000, and Board-approved professional services consultant contracts with amendments exceeding 5%, but not exceeding 15% will be reported to the Board at its next scheduled meeting. 
[bookmark: _Hlk131407635]The intent of this report is to provide the Board of Trustees a review of those contract changes germane to the above criteria for capital projects.
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BOARD APPROVED CONSTRUCTION CONTRACTS WITH 
CUMULATIVE CHANGE ORDERS > $1 MILLION

University: Urbana-Champaign
	
	
	




	
	
	



Project # / Title: U20118 – Undergraduate Library Redevelopment

Vendor: Williams Bros. Construction, Inc.
Contract Type: Single Prime
Original Contract Value: $41,878,000.00
Change Orders to Date ($ / %): $2,880,745.85 / 6.9%
Current Contract Value: $44,758,745.85


Project Description: 
The Undergraduate Library Redevelopment will transform the former Undergraduate Library into the Archives and Special Collections Building while preserving its distinctive architectural character. Renovations will provide modern spaces for archival storage, preservation, access, instruction, research, and public engagement, supporting the long-term stewardship and use of the University’s unique collections.

BOT Approval History:

 


Planned Vendor Utilization:
	Awarded Vendor
	Prime Contract $ / Diverse Subcontractor Certification
	Certified Subcontractor - Original Contract Value
	 % of Contract
	Certified Subcontractor - Current Contract Value
	 % of Contract

	Williams Brothers Construction
	MBE (AFA)
	$2,415,000
	5%
	$2,446,974
	5%

	Peoria Heights, IL
	MBE (HA)
	$1,524,100
	4%
	$1,571,683
	4%

	Original Contract Value
	VOSB
	$1,257,000
	3%
	$1,426,622
	3%

	 $41,878,000
	WMBE (AFA)
	$385,000
	1%
	$309,864
	1%

	Current Contract Value
	WBE
	$8,269,500
	20%
	$8,926,484
	20%

	$44,758,746
	 
	$13,850,600
	33%
	$14,681,627
	33%








University: Urbana-Champaign
Project # / Title: U21076 – Veterinary Teaching Hospital – Small Animal Clinic Oncology Center Addition – Design & Construction
Vendor: Broeren Russo Construction, Inc.
Contract Type: Single Prime
Original Contract Value: $20,425,000.00
Change Orders to Date ($ / %): $1,271,756.93 / 6.2%
Current Contract Value: $21,696,756.93

Project Description: 
This project will construct a 23,227-square-foot addition to the Small Animal Clinic at the Veterinary Teaching Hospital to expand the University’s capacity for veterinary oncology services and meet growing demand for specialized cancer treatment. The new Oncology Center will provide modern clinical space dedicated to the diagnosis, treatment, and care of animal patients while supporting the teaching, research, and service missions of the College of Veterinary Medicine.

BOT Approval History:




Planned Vendor Utilization:
	Awarded Vendor
	Prime Contract $ / Diverse Subcontractor Certification
	Certified Subcontractor - Original Contract Value
	% of Contract
	Certified Subcontractor - Current Contract Value
	% of Contract

	Broeren Russo Builders, Inc.
	
	
	
	
	

	Champaign, IL
	MBE (AFA)
	$0
	0%
	$0
	0%

	Original Contract Value
	MBE (HA)
	$5,440,791
	27%
	$7,500,639
	35%

	$20,425,000 
	VOSB
	$614,957
	3%
	$503,832
	2%

	Current Contract Value
	WBE
	$739,000
	4%
	$746,857
	3%

	$21,696,757
	
	$6,794,748
	33%
	$8,751,328
	40%






BOARD APPROVED PSC CONTRACTS WITH 
CUMULATIVE AMENDMENTS > 5%

No reportable amendments in this Board cycle.

January 2022  Project Approval


January 2022   Design Approval


March 2025    Budget and Construction Contract Approval


July 2021   Project Approval


July 2023   Design Approval


July 2024    Budget and Construction Contract Approval
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